## Information
Summary
This Risk Register has been developed for a mid-size SaaS Technology Company to identify, assess, and manage potential risks that could impact organizational operations, data security, and service delivery. The register captures key risks across multiple categories including Data Breach, Ransomware, Insider Threats, System Vulnerabilities, Social Engineering, Identity and Access, Supply Chain, Non-compliance, Operational Disruption, and Response & Recovery. Each risk is evaluated based on its Impact and Likelihood, with inherent and residual risk levels calculated to prioritize mitigation actions. The register also assigns clear risk ownership, establishes control measures, and defines review timelines to ensure continuous monitoring and improvement. This structured approach supports governance, risk management, and compliance (GRC) efforts, helping the organization maintain operational resilience, protect sensitive data, and comply with industry standards and regulations.
RISK DASHBOARD
akiratech.ca

## Dashboard
LIKELIHOOD | Highly Likely | 5 | 2 | 2 | 3 | 2 | 2
| Likely | 4 | 1 | 0 | 0 | 1 | 0
| Possible | 3 | 1 | 0 | 0 | 1 | 1
| Unlikely | 2 | 0 | 0 | 0 | 0 | 0
| Rare | 1 | 0 | 0 | 0 | 0 | 1
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | Very Low | Low | Moderate | High | Very High
IMPACT
Active Risks - by Risk Levels
Shows the number of risks according to each Level
Active Risks
Total risks under active management
17
Mitigated Risks
Percentage of risks that are mitigated so far
5%
RISK DASHBOARD
Risk Heatmap
Heatmap showing all Active Risks
Risk above tolerance
% of risks that exceed the tolerance level
85%
Accepted Risks
Percentage of risks that have been accepted
10%
Overdue Risks
Number of risks that are overdue
12
Risk Categories
Shows the count of active risks under each Category
New risks reported
Risks reported per month
Average Risk Score
Shows the average of all risks, over a 12 month period

## Heatmap (hidden)
LIKELIHOOD | Highly Likely | 5 | 10 | 15 | 20 | 25
| Likely | 4 | 8 | 12 | 16 | 20
| Possible | 3 | 6 | 9 | 12 | 15
| Unlikely | 2 | 4 | 6 | 8 | 10
| Rare | 1 | 2 | 3 | 4 | 5
|  | Very Low | Low | Moderate | High | Very High
IMPACT

## Gantt chart
| Gantt start | 2024-01-01
| Interval (months) | 1
Risks | Start | Due | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
1 - Risk 1 | 2024-04-09 | 2024-11-23 | bar: 2024-05-01 to 2024-11-01
2 - Risk 2 | 2024-02-03 | 2024-10-12 | bar: 2024-03-01 to 2024-10-01
3 - Risk 3 | 2024-02-04 | 2024-11-02 | bar: 2024-03-01 to 2024-11-01
4 - Risk 4 | 2024-02-17 | 2024-08-11 | bar: 2024-03-01 to 2024-08-01
RISK GANTT CHART

## Risk Register
| Risk Identification | [9 empty] | Risk Analysis | [5 empty] | Risk Response |  | Residual Risk | [5 empty] | Tracking | [5 empty] | Calculations for Pivots
Risk ID | Risk Title | Risk Description | Created Date | Cause | Consequence | Risk Category | Risk comments | Department | Risk Owner | Existing measures and controls | Inherent Impact Level | Inherent Impact Rating | Inherent Likelihood Level | Inherent Likelihood Rating | Inherent Risk Level | Inherent Risk Rating | Risk Response Strategy | New measures and controls | Residual Impact Level | Residual Impact Rating | Residual Likelihood Level | Residual Likelihood Rating | Residual Risk Level | Residual Risk Rating | Risk Status | Status comments | Risk Due Date | Risk Close Date | Overdue? | Next Review Date | Due Month | Created Month | Risk-Change-Date | Corrected-Risk-Change-Date | Inherent-I-L-Combo | Residual-I-L-Combo | Mitigated? | Current-Impact | Current-Likelihood | Current-I-L-Combo | Current Risk Level
1 | Risk 1 | sec1 | 2024-02-05 | sec1 | sec1 | Data breach | Monitoring required for perimeter security | Information Technology (IT) | IT Security Manager | Firewall, Antivirus, Access Control | Very Low | 1 | Highly Likely | 5 | Medium | 5 | Accept | Continuous monitoring implementation | Very Low | 1 | Highly Likely | 5 | Medium | 5 | Open | Risk accepted by management |  |  | Missing Risk Due Date | 2024-06-30 | Missing Risk Due Date | Feb-2024 | 0 | 2030-01-01 | Very Low-Highly Likely | Very Low-Highly Likely | No | Very Low | Highly Likely | Very Low-Highly Likely | Medium
2 | Risk 2 | sec2 | 2024-05-02 | sec2 | sec2 | Ransomware | Endpoint exposure risk | Information Technology (IT) | IT Operations Manager | Endpoint protection, Backups | Low | 2 | Likely | 4 | Medium | 8 | Accept | Enhanced ransomware detection | Low | 2 | Likely | 4 | Medium | 8 | Closed | Risk formally closed |  | 2024-07-15 | Missing Risk Due Date | 2024-06-30 | Missing Risk Due Date | May-2024 | 2024-07-15 | 2024-07-15 | Low-Likely | Low-Likely | No | Low | Likely | Low-Likely | Medium
3 | Risk 3 | sec3 | 2024-04-03 | sec3 | sec3 | Insider Threats | Privileged access risk identified | Information Technology (IT) | IT Security Manager | Access reviews, Logging | Moderate | 3 | Highly Likely | 5 | Medium | 15 | Mitigate | Implement PAM solution | Very Low | 1 | Likely | 4 | Low | 4 | In Progress | Mitigation in progress | 2024-05-08 |  | Overdue | 2024-06-30 | 2024-05 | Apr-2024 | 2024-05-08 | 2024-05-08 | Moderate-Highly Likely | Very Low-Likely | No | Moderate | Highly Likely | Moderate-Highly Likely | Medium
4 | Risk 4 | sec4 | 2024-04-04 | sec4 | sec4 | Supply Chain | Third-party dependency risk | Procurement | Vendor Manager | Vendor assessments | High | 4 | Likely | 4 | Medium | 16 | Mitigate | Strengthen supplier due diligence | Very Low | 1 | Unlikely | 2 | Low | 2 | Open | Monitoring supplier compliance |  |  | Missing Risk Due Date | 2024-09-30 | Missing Risk Due Date | Apr-2024 | 0 | 2030-01-01 | High-Likely | Very Low-Unlikely | No | High | Likely | High-Likely | Medium
5 | Risk 5 | sec5 | 2024-04-05 | sec5 | sec5 | System Vulnerabilities | Patch management gaps identified | Information Technology (IT) | IT Infrastructure Manager | Vulnerability scans | Very High | 5 | Highly Likely | 5 | High | 25 | Mitigate | Accelerated patch cycle | Low | 2 | Likely | 4 | Medium | 8 | In Progress | Remediation ongoing | 2024-02-06 |  | Overdue | 2024-06-30 | 2024-02 | Apr-2024 | 2024-02-06 | 2024-02-06 | Very High-Highly Likely | Low-Likely | No | Very High | Highly Likely | Very High-Highly Likely | High
6 | Risk 6 | sec6 | 2024-04-06 | sec6 | sec6 | Social Engineering | Phishing exposure observed | Human Resources (HR) | IT Security Manager | Awareness training | Very Low | 1 | Likely | 4 | Low | 4 | Mitigate | Simulated phishing campaigns | Very Low | 1 | Unlikely | 2 | Low | 2 | In Progress | Controls being enhanced | 2023-10-19 |  | Overdue | 2024-06-30 | 2023-10 | Apr-2024 | 2023-10-19 | 2023-10-19 | Very Low-Likely | Very Low-Unlikely | No | Very Low | Likely | Very Low-Likely | Low
7 | Risk 7 | sec7 | 2024-04-07 | sec7 | sec7 | Identity and Access | Excessive privileged accounts | Information Technology (IT) | IAM Manager | Role-based access | Very High | 5 | Rare | 1 | Medium | 5 | Mitigate | MFA implementation | Very Low | 1 | Rare | 1 | Low | 1 | In Progress | Access review ongoing | 2023-09-11 |  | Overdue | 2024-06-30 | 2023-09 | Apr-2024 | 2023-09-11 | 2023-09-11 | Very High-Rare | Very Low-Rare | No | Very High | Rare | Very High-Rare | Medium
8 | Risk 8 | sec8 | 2024-04-08 | sec8 | sec8 | Non-compliance | Minor compliance gaps | Legal / Compliance | Compliance Officer | Policy framework | Low | 2 | Unlikely | 2 | Low | 4 | Mitigate | Control self-assessment | Low | 2 | Unlikely | 2 | Low | 4 | Closed | Risk mitigated and closed |  |  | Missing Risk Due Date | 2024-06-30 | Missing Risk Due Date | Apr-2024 | 0 | 2030-01-01 | Low-Unlikely | Low-Unlikely | Yes | Low | Unlikely | Low-Unlikely | Low
9 | Risk 9 | sec9 | 2024-04-09 | sec9 | sec9 | Non-compliance | Regulatory monitoring required | Legal / Compliance | Sales Director | Contract reviews | High | 4 | Possible | 3 | Medium | 12 | Mitigate | Compliance checklist rollout | Very Low | 1 | Likely | 4 | Low | 4 | Open | Risk under observation |  |  | Missing Risk Due Date | 2024-09-30 | Missing Risk Due Date | Apr-2024 | 0 | 2030-01-01 | High-Possible | Very Low-Likely | No | High | Possible | High-Possible | Medium
10 | Risk 10 | sec10 | 2024-04-10 | sec10 | sec10 | Data breach | Customer data handling risk | Information Technology (IT) | Sales Director | Data encryption | Very High | 5 | Possible | 3 | Medium | 15 | Mitigate | DLP solution deployment | Low | 2 | Likely | 4 | Medium | 8 | Open | Risk mitigation planned |  |  | Missing Risk Due Date | 2024-09-30 | Missing Risk Due Date | Apr-2024 | 0 | 2030-01-01 | Very High-Possible | Low-Likely | No | Very High | Possible | Very High-Possible | Medium
11 | Risk 11 | sec11 | 2024-04-11 | sec11 | sec11 | Ransomware | Backup integrity verified | Information Technology (IT) | IT Operations Manager | Backup testing | Very Low | 1 | Possible | 3 | Low | 3 | Mitigate | Ransomware tabletop exercise | Very Low | 1 | Likely | 4 | Low | 4 | In Progress | Monitoring effectiveness | 2024-10-02 |  | Overdue | 2024-12-31 | 2024-10 | Apr-2024 | 2024-10-02 | 2024-10-02 | Very Low-Possible | Very Low-Likely | No | Very Low | Possible | Very Low-Possible | Low
12 | Risk 12 | sec12 | 2024-04-12 | sec12 | sec12 | Insider Threats | Insider activity monitoring | Human Resources (HR) | Sales Director | Access logs review | Low | 2 | Highly Likely | 5 | Medium | 10 | Mitigate | Segregation of duties enforcement | Very Low | 1 | Likely | 4 | Low | 4 | In Progress | Mitigation ongoing | 2024-11-30 |  | Overdue | 2024-12-31 | 2024-11 | Apr-2024 | 2024-11-30 | 2024-11-30 | Low-Highly Likely | Very Low-Likely | No | Low | Highly Likely | Low-Highly Likely | Medium
13 | Risk 13 | sec13 | 2024-05-13 | sec13 | sec13 | Supply Chain | Supplier contract dependency | Procurement | Finance Manager | Contract controls | Moderate | 3 | Highly Likely | 5 | Medium | 15 | Mitigate | Financial contingency planning | Low | 2 | Likely | 4 | Medium | 8 | In Progress | Mitigation in progress | 2024-12-05 |  | Overdue | 2024-12-31 | 2024-12 | May-2024 | 2024-12-05 | 2024-12-05 | Moderate-Highly Likely | Low-Likely | No | Moderate | Highly Likely | Moderate-Highly Likely | Medium
14 | Risk 14 | sec14 | 2024-04-14 | sec14 | sec14 | System Vulnerabilities | Critical system exposure | Information Technology (IT) | Legal Counsel | System hardening | High | 4 | Highly Likely | 5 | High | 20 | Mitigate | Security audit execution | Very Low | 1 | Likely | 4 | Low | 4 | In Progress | Urgent remediation required | 2024-01-19 |  | Overdue | 2024-06-30 | 2024-01 | Apr-2024 | 2024-01-19 | 2024-01-19 | High-Highly Likely | Very Low-Likely | No | High | Highly Likely | High-Highly Likely | High
15 | Risk 15 | sec15 | 2024-09-15 | sec15 | sec15 | Social Engineering | High phishing susceptibility | Human Resources (HR) | Procurement Manager | Awareness sessions | Very High | 5 | Highly Likely | 5 | High | 25 | Mitigate | Email filtering enhancement | Low | 2 | Likely | 4 | Medium | 8 | In Progress | Controls being strengthened | 2024-06-06 |  | Overdue | 2024-09-30 | 2024-06 | Sep-2024 | 2024-06-06 | 2024-06-06 | Very High-Highly Likely | Low-Likely | No | Very High | Highly Likely | Very High-Highly Likely | High
16 | Risk 16 | sec16 | 2024-04-16 | sec16 | sec16 | Identity and Access | Weak password practices | Information Technology (IT) | IT Security Manager | Password policy | Very Low | 1 | Highly Likely | 5 | Medium | 5 | Mitigate | Enforce MFA enterprise-wide | Very Low | 1 | Unlikely | 2 | Low | 2 | In Progress | IAM improvements ongoing | 2024-12-12 |  | Overdue | 2024-12-31 | 2024-12 | Apr-2024 | 2024-12-12 | 2024-12-12 | Very Low-Highly Likely | Very Low-Unlikely | No | Very Low | Highly Likely | Very Low-Highly Likely | Medium
17 | Risk 17 | sec17 | 2024-04-17 | sec17 | sec17 | Non-compliance | Compliance reporting gaps | Legal / Compliance | IT Security Manager | Internal audits | Low | 2 | Highly Likely | 5 | Medium | 10 | Mitigate | Automated compliance dashboard | Low | 2 | Likely | 4 | Medium | 8 | In Progress | Remediation ongoing | 2024-04-11 |  | Overdue | 2024-06-30 | 2024-04 | Apr-2024 | 2024-04-11 | 2024-04-11 | Low-Highly Likely | Low-Likely | No | Low | Highly Likely | Low-Highly Likely | Medium
18 | Risk 18 | sec18 | 2024-04-18 | sec18 | sec18 | System Vulnerabilities | Delayed patch cycles | Information Technology (IT) | IT Infrastructure Manager | Monthly patching | Moderate | 3 | Highly Likely | 5 | Medium | 15 | Mitigate | Increase scan frequency | Moderate | 3 | Unlikely | 2 | Medium | 6 | In Progress | Monitoring remediation | 2023-12-19 |  | Overdue | 2024-06-30 | 2023-12 | Apr-2024 | 2023-12-19 | 2023-12-19 | Moderate-Highly Likely | Moderate-Unlikely | No | Moderate | Highly Likely | Moderate-Highly Likely | Medium
19 | Risk 19 | sec19 | 2024-04-19 | sec19 | sec19 | System Vulnerabilities | Critical vulnerabilities detected | Information Technology (IT) | IT Infrastructure Manager | Vulnerability scanning | High | 4 | Highly Likely | 5 | High | 20 | Mitigate | Immediate patch deployment | Very Low | 1 | Likely | 4 | Low | 4 | In Progress | High priority remediation | 2023-12-12 |  | Overdue | 2024-06-30 | 2023-12 | Apr-2024 | 2023-12-12 | 2023-12-12 | High-Highly Likely | Very Low-Likely | No | High | Highly Likely | High-Highly Likely | High
20 | Risk 20 | sec20 | 2024-12-20 | sec20 | sec20 | System Vulnerabilities | Risk formally accepted by board | Executive / IT Governance | CIO | Existing controls maintained | Very High | 5 | Highly Likely | 5 | High | 25 | Accept | No additional controls planned | Very High | 5 | Highly Likely | 5 | High | 25 | Closed | Risk closed and accepted |  | 2024-07-01 | Missing Risk Due Date | 2024-12-31 | Missing Risk Due Date | Dec-2024 | 2024-07-01 | 2024-07-01 | Very High-Highly Likely | Very High-Highly Likely | No | Very High | Highly Likely | Very High-Highly Likely | High
21 | [5 empty] | -- Select Risk Category -- |  | -- select department -- |  |  | -- Select Impact -- | --- Error --- | -- Select Likelihood -- | --- Error --- | -- Error -- | -- Error -- | -- Select Risk Response -- |  | -- Select Impact -- | --- Error --- | -- Select Likelihood -- | --- Error --- | -- Error -- | -- Error -- | -- Select Risk Status -- |  |  |  | Missing Risk Due Date |  | Missing Risk Due Date | Created Date missing | 0 | 2030-01-01 | -- Select Impact ----- Select Likelihood -- | -- Select Impact ----- Select Likelihood -- | Error | -- Select Impact -- | -- Select Likelihood -- | -- Select Impact ----- Select Likelihood -- | -- Error --
Formulas:
Overdue? = IF(ISBLANK(RiskRegister[[#This Row],[Risk Due Date]]), "Missing Risk Due Date", IF(RiskRegister[[#This Row],[Risk Due Date]] < TODAY(), "Overdue", "Not Overdue"))
Risk-Change-Date = IF(RiskRegister[[#This Row],[Risk Status]]="Closed",RiskRegister[[#This Row],[Risk Close Date]],RiskRegister[[#This Row],[Risk Due Date]])
Corrected-Risk-Change-Date = IF(RiskRegister[[#This Row],[Risk-Change-Date]]=0,DATE(2030,1,1),RiskRegister[[#This Row],[Risk-Change-Date]])
RISK REGISTER

## Tasks
[8 empty] | Related Risks |  | Calculations for Pivots
Task ID | Created Date | Task Title | Task Description | Assignee | Status | Due Date | Comments | Risk ID | Risk Title | Overdue? | Due Month | Due Year | Risk-ID-Title-Combo | Residual-I-L-Combo | Mitigated? | Current Risk LRonl
TASK-001 | 2024-04-09 | Implement New Firewall | Deployed and configured a new firewall to enhance perimeter security and enforce network access controls. | Ron | Closed | 2024-04-18 | Pending review. | 1 | Risk 1 | No | April | 2024 | 1 - Risk 1
TASK-002 | 2024-02-10 | Update Documentation | Reviewed and updated security policies and procedural documents to ensure regulatory alignment. | Shane | Closed | 2024-09-03 | No comments | 2 | Risk 2 | No | February | 2024 | 2 - Risk 2
TASK-003 | 2024-02-09 | Conduct Risk Assessment | Performed risk assessment to identify, evaluate, and document organizational security risks. | Ron | In Progress | 2024-07-31 | Pending review. | 3 | Risk 3 | Yes | February | 2024 | 3 - Risk 3
TASK-004 | 2024-04-09 | Employee Training | Conducted security awareness training covering data protection and acceptable use policies. | Shane | In Progress | 2024-05-27 | Pending review. | 1 | Risk 1 | Yes | April | 2024 | 1 - Risk 1
TASK-005 | 2024-02-27 | Conduct Risk Assessment | Assessed departmental risks and updated risk register with mitigation plans. | Rendle | Closed | 2024-04-24 | Pending review. | 2 | Risk 2 | No | February | 2024 | 2 - Risk 2
TASK-006 | 2024-02-17 | Conduct Risk Assessment | Evaluated IT asset risks and recommended control improvements. | Shane | In Progress | 2024-08-11 | Pending review. | 4 | Risk 4 | Yes | February | 2024 | 4 - Risk 4
TASK-007 | 2024-04-09 | Review Security Policies | Reviewed and revised security policies to ensure compliance with current standards and regulations. | Bolla | In Progress | 2024-11-01 | Pending review. | 1 | Risk 1 | Yes | April | 2024 | 1 - Risk 1
TASK-008 | 2024-02-22 | Update Documentation | Updated process documentation to reflect recent control and system changes. | Ron | On Hold | 2024-08-11 | Pending review. | 2 | Risk 2 | Yes | February | 2024 | 2 - Risk 2
TASK-009 | 2024-02-21 | Conduct Risk Assessment | Conducted risk analysis for critical systems and documented treatment actions. | Shane | Not Started | 2024-02-07 | Pending review. | 3 | Risk 3 | Yes | February | 2024 | 3 - Risk 3
TASK-010 | 2024-04-09 | Implement new tool | Implemented security monitoring tool to improve threat detection and incident response capabilities. | Harold | Not Started | 2024-08-26 | Pending review. | 1 | Risk 1 | Yes | April | 2024 | 1 - Risk 1
TASK-011 | 2024-02-04 | Employee Training | Delivered compliance and information security training to employees. | Rendle | On Hold | 2024-08-20 | No comments | 2 | Risk 2 | Yes | February | 2024 | 2 - Risk 2
TASK-012 | 2024-02-14 | Implement new tool | Deployed governance tool to streamline risk tracking and reporting. | Ron | In Progress | 2024-02-21 | No comments | 3 | Risk 3 | Yes | February | 2024 | 3 - Risk 3
TASK-013 | 2024-04-09 | Implement new tool | Integrated new compliance management system into existing processes. | Shane | Closed | 2024-11-10 | Pending review. | 1 | Risk 1 | No | April | 2024 | 1 - Risk 1
TASK-014 | 2024-04-09 | Implement new tool | Configured and tested security tool to enhance control monitoring. | Shane | Closed | 2024-02-15 | Pending review. | 1 | Risk 1 | No | April | 2024 | 1 - Risk 1
TASK-015 | 2024-02-24 | Employee Training | Conducted role-based training focused on secure handling of sensitive information. | Bolla | Closed | 2024-10-12 | Pending review. | 2 | Risk 2 | No | February | 2024 | 2 - Risk 2
TASK-016 | 2024-02-26 | Review Security Policies | Reviewed access control and data protection policies for effectiveness and compliance. | Harold | Not Started | 2024-01-01 | No comments | 2 | Risk 2 | Yes | February | 2024 | 2 - Risk 2
TASK-017 | 2024-02-27 | Review Security Policies | Updated incident response and business continuity policies. | Ron | On Hold | 2024-11-02 | Pending review. | 3 | Risk 3 | Yes | February | 2024 | 3 - Risk 3
TASK-018 | 2024-02-04 | Implement new tool | Implemented vulnerability management tool to support continuous security assessment. | Ron | Closed | 2024-02-26 | Pending review. | 3 | Risk 3 | No | February | 2024 | 3 - Risk 3
TASK-019 | 2024-04-09 | Employee Training | Facilitated refresher training on cybersecurity awareness and phishing prevention. | Rendle | Closed | 2024-11-23 | No comments | 1 | Risk 1 | No | April | 2024 | 1 - Risk 1
TASK-020 | 2024-02-03 | Employee Training | Conducted onboarding security training for new employees. | Rendle | In Progress | 2024-06-14 | Pending review. | 2 | Risk 2 | Yes | February | 2024 | 2 - Risk 2
TASK-021 | [8 empty] | Error! | Error |  |  | - Error!
TASK-022 | [8 empty] | Error! | Error |  |  | - Error!
TASK-023 | [8 empty] | Error! | Error |  |  | - Error!
TASK-024 | [8 empty] | Error! | Error |  |  | - Error!
TASK-025 | [8 empty] | Error! | Error |  |  | - Error!
TASK-026 | [8 empty] | Error! | Error |  |  | - Error!
TASK-027 | [8 empty] | Error! | Error |  |  | - Error!
TASK-028 | [8 empty] | Error! | Error |  |  | - Error!
TASK-029 | [8 empty] | Error! | Error |  |  | - Error!
TASK-030 | [8 empty] | Error! | Error |  |  | - Error!
TASK-031 | [8 empty] | Error! | Error |  |  | - Error!
TASK-032 | [8 empty] | Error! | Error |  |  | - Error!
TASK-033 | [8 empty] | Error! | Error |  |  | - Error!
TASK-034 | [8 empty] | Error! | Error |  |  | - Error!
TASK-035 | [8 empty] | Error! | Error |  |  | - Error!
TASK-036 | [8 empty] | Error! | Error |  |  | - Error!
TASK-037 | [8 empty] | Error! | Error |  |  | - Error!
TASK-038 | [8 empty] | Error! | Error |  |  | - Error!
TASK-039 | [8 empty] | Error! | Error |  |  | - Error!
TASK-040 | [8 empty] | Error! | Error |  |  | - Error!
TASK-041 | [8 empty] | Error! | Error |  |  | - Error!
TASK-042 | [8 empty] | Error! | Error |  |  | - Error!
TASK-043 | [8 empty] | Error! | Error |  |  | - Error!
TASK-044 | [8 empty] | Error! | Error |  |  | - Error!
TASK-045 | [8 empty] | Error! | Error |  |  | - Error!
TASK-046 | [8 empty] | Error! | Error |  |  | - Error!
TASK-047 | [8 empty] | Error! | Error |  |  | - Error!
TASK-048 | [8 empty] | Error! | Error |  |  | - Error!
TASK-049 | [8 empty] | Error! | Error |  |  | - Error!
TASK-050 | [8 empty] | Error! | Error |  |  | - Error!
TASK-051 | [8 empty] | Error! | Error |  |  | - Error!
TASK-052 | [8 empty] | Error! | Error |  |  | - Error!
TASK-053 | [8 empty] | Error! | Error |  |  | - Error!
TASK-054 | [8 empty] | Error! | Error |  |  | - Error!
TASK-055 | [8 empty] | Error! | Error |  |  | - Error!
TASK-056 | [8 empty] | Error! | Error |  |  | - Error!
TASK-057 | [8 empty] | Error! | Error |  |  | - Error!
TASK-058 | [8 empty] | Error! | Error |  |  | - Error!
TASK-059 | [8 empty] | Error! | Error |  |  | - Error!
TASK-060 | [8 empty] | Error! | Error |  |  | - Error!
TASK-061 | [8 empty] | Error! | Error |  |  | - Error!
TASK-062 | [8 empty] | Error! | Error |  |  | - Error!
TASK-063 | [8 empty] | Error! | Error |  |  | - Error!
TASK-064 | [8 empty] | Error! | Error |  |  | - Error!
TASK-065 | [8 empty] | Error! | Error |  |  | - Error!
TASK-066 | [8 empty] | Error! | Error |  |  | - Error!
TASK-067 | [8 empty] | Error! | Error |  |  | - Error!
TASK-068 | [8 empty] | Error! | Error |  |  | - Error!
TASK-069 | [8 empty] | Error! | Error |  |  | - Error!
TASK-070 | [8 empty] | Error! | Error |  |  | - Error!
TASK-071 | [8 empty] | Error! | Error |  |  | - Error!
TASK-072 | [8 empty] | Error! | Error |  |  | - Error!
TASK-073 | [8 empty] | Error! | Error |  |  | - Error!
TASK-074 | [8 empty] | Error! | Error |  |  | - Error!
TASK-075 | [8 empty] | Error! | Error |  |  | - Error!
TASK-076 | [8 empty] | Error! | Error |  |  | - Error!
TASK-077 | [8 empty] | Error! | Error |  |  | - Error!
TASK-078 | [8 empty] | Error! | Error |  |  | - Error!
TASK-079 | [8 empty] | Error! | Error |  |  | - Error!
TASK-080 | [8 empty] | Error! | Error |  |  | - Error!
TASK-081 | [8 empty] | Error! | Error |  |  | - Error!
TASK-082 | [8 empty] | Error! | Error |  |  | - Error!
TASK-083 | [8 empty] | Error! | Error |  |  | - Error!
TASK-084 | [8 empty] | Error! | Error |  |  | - Error!
TASK-085 | [8 empty] | Error! | Error |  |  | - Error!
TASK-086 | [8 empty] | Error! | Error |  |  | - Error!
TASK-087 | [8 empty] | Error! | Error |  |  | - Error!
TASK-088 | [8 empty] | Error! | Error |  |  | - Error!
TASK-089 | [8 empty] | Error! | Error |  |  | - Error!
TASK-090 | [8 empty] | Error! | Error |  |  | - Error!
TASK-091 | [8 empty] | Error! | Error |  |  | - Error!
TASK-092 | [8 empty] | Error! | Error |  |  | - Error!
TASK-093 | [8 empty] | Error! | Error |  |  | - Error!
TASK-094 | [8 empty] | Error! | Error |  |  | - Error!
TASK-095 | [8 empty] | Error! | Error |  |  | - Error!
TASK-096 | [8 empty] | Error! | Error |  |  | - Error!
TASK-097 | [8 empty] | Error! | Error |  |  | - Error!
TASK-098 | [8 empty] | Error! | Error |  |  | - Error!
TASK-099 | [8 empty] | Error! | Error |  |  | - Error!
TASK-100 | [8 empty] | Error! | Error |  |  | - Error!
Formulas:
Overdue? = IF(OR([Status]="", [Due Date]=""), "Error", IF(AND([Status]<>"Closed", [Due Date]<=TODAY()), "Yes", "No"))
Overdue? = IF(OR([Status, row above]="", [Due Date]=""), "Error", IF(AND([Status, row above]<>"Closed", [Due Date]<=TODAY()), "Yes", "No"))
Task Tracker for Risks

## RiskPivots
Inherent Risk Levels and Ratings
Note: 1) In both the below Pivot tables, the rows where Inherent Risk is not calculated is excluded ( "-- Error --") 2) The Risk Rating table is used for updating the Heatmaps
Inherent Risk Level | Count |  | Inherent Risk Rating | Count
High | 5 |  | 3 | 1
Low | 3 |  | 4 | 2
Medium | 12 |  | 5 | 3
Grand Total | 20 |  | 8 | 1
|  |  | 10 | 2
|  |  | 12 | 1
|  |  | 15 | 4
|  |  | 16 | 1
|  |  | 20 | 2
|  |  | 25 | 3
|  |  | Grand Total | 20
Residual Risk Levels and Ratings
Note: in both the below Pivot tables, the rows where Inherent Risk is not calculated is excluded ( "-- Error --")
Residual Risk Level | Count |  | Residual Risk Rating | Count
High | 1 |  | 2 | 3
Medium | 8 |  | 4 | 7
Low | 11 |  | 5 | 1
-- Error -- | 980 |  | 6 | 1
Grand Total | 1000 |  | 8 | 6
|  |  | 25 | 1
|  |  | Grand Total | 19
Combined Inherent and Residual Risk
This table takes the data from the above two pivot tables and is used for the chart
| Inherent Risks | Residual Risks
High | 5 | 1
Low | 3 | 11
Medium | 12 | 8
Current Risk Level
Risk level based on the status of the risk. If its closed, then the residual risk is returned, else the inherent risk is returned. Based on the Current Risk Level column in Calculations for Pivots section in the Risk Register.
Risk Status | Count
High | 5
Low | 3
Medium | 12
Grand Total | 20
Risks above threshold
Risk level based on the status of the risk. This is calculated from the Pivot in "Current Risk Level" section. Note: In this case, the unacceptable risks are High and Medium. Based on your risk appetite, please make appropriate changes
Risk Status | Count
High | 5
Medium | 12
Grand Total | 17 |  | 17 | 85%
Mitigated Risks
Number of risks that are mitigated as a percentage of the total. Errors are filtered out
Mitigated? | Count
No | 95% |  | Mitigated Risks
Yes | 5% |  | 5%
Grand Total | 100%
Status of all risks
Status of all risks excluding the ones where the status is not selected
Risk Status | Count
Open | 4
In Progress | 13
Closed | 3
Grand Total | 20
Total active risks
Sum of all 'Open' and 'In Progress' statuses, calculated from the above pivot. If you add new statuses, update the formula
Total active risks | 17
Status of all Mitigated and Accepted risks
Status of all risks where the Risk Response is either Mitigation or Acceptance. Excludes the ones where the status is not selected
Count | Risk Response Strategy
Risk Status | Accept | Mitigate | Grand Total
Open | 1 | 3 | 4
In Progress | 0 | 13 | 13
Closed | 2 | 1 | 3
Grand Total | 3 | 17 | 20
Total accepted risks
Count of Risk with 'Closed' status and Risk Response Strategy as "Accept" calculated from the above pivot. If you add new statuses, update the formula
Total accepted risks | 2
% accepted risks | 10%
Overdue Risks
Count of risks with In Progress status that have exceeded the due date
Risk Status | In Progress
Risk Status | Count of Risk ID |  | Total risks overdue | 12
Overdue | 12
Not Overdue | 1
Grand Total | 13
Total active risks by Risk Response
Sum of all 'Open' and 'In Progress' statuses for ones where Risk Response is either Mitigation or Acceptance, calculated from the above pivot. If you add new statuses, update the formula
| Accept | Mitigate | Total
Total active risks | 1 | 16 | 17
Heatmap calculation for Current Risks
The 1st table filters only the active risks The 2nd table is used to populate the Heatmap for Risks Make sure the count matches with the total active risks value
Risk Status | (Multiple Items)
Current-I-L-Combo | Count |  | Very Low-Highly Likely | 2
High-Highly Likely | 2 |  | Very Low-Likely | 1
High-Likely | 1 |  | Very Low-Possible | 1
High-Possible | 1 |  | Very Low-Unlikely | 0
Low-Highly Likely | 2 |  | Very Low-Rare | 0
Moderate-Highly Likely | 3 |  | Low-Highly Likely | 2
Very High-Highly Likely | 2 |  | Low-Likely | 0
Very High-Possible | 1 |  | Low-Possible | 0
Very High-Rare | 1 |  | Low-Unlikely | 0
Very Low-Highly Likely | 2 |  | Low-Rare | 0
Very Low-Likely | 1 |  | Moderate-Highly Likely | 3
Very Low-Possible | 1 |  | Moderate-Likely | 0
Grand Total | 17 |  | Moderate-Possible | 0
|  |  | Moderate-Unlikely | 0
|  |  | Moderate-Rare | 0
|  |  | High-Highly Likely | 2
|  |  | High-Likely | 1
|  |  | High-Possible | 1
|  |  | High-Unlikely | 0
|  |  | High-Rare | 0
|  |  | Very High-Highly Likely | 2
|  |  | Very High-Likely | 0
|  |  | Very High-Possible | 1
|  |  | Very High-Unlikely | 0
|  |  | Very High-Rare | 1
|  |  | Total | 17
Active risk categories
Categories of risks which are actively managed. Only risks with Open and In Progress states are considered.
Risk Status | (Multiple Items)
Risk Status | Count
Ransomware | 1
Non-compliance | 2
Identity and Access | 2
Social Engineering | 2
Data breach | 2
Supply Chain | 2
Insider Threats | 2
System Vulnerabilities | 4
Grand Total | 17
Risks by created date
The 1st table filters only the active risks The 2nd table is used to populate the Heatmap for Risks Make sure the count matches with the total active risks value
Created Month | Count |  | Jan-2024 | 1
Created Date missing | 980 |  | Feb-2024 | 0
Jan-2024 | 1 |  | Mar-2024 | 0
Apr-2024 | 16 |  | Apr-2024 | 16
May-2024 | 1 |  | May-2024 | 1
Sep-2024 | 1 |  | Jun-2024 | 0
Dec-2024 | 1 |  | Jul-2024 | 0
Grand Total | 1000 |  | Aug-2024 | 0
|  |  | Sep-2024 | 1
|  |  | Oct-2024 | 0
|  |  | Nov-2024 | 0
|  |  | Dec-2024 | 1
|  |  | Total | 20
Average Risk Score over time
This takes data from the RiskTimeline sheet in a table format useful for a chart
2024-01-01 | 11.3
2024-02-01 | 10.5
2024-03-01 | 9.65
2024-04-01 | 9.65
2024-05-01 | 9.55
2024-06-01 | 9
2024-07-01 | 8.15
2024-08-01 | 8.15
2024-09-01 | 8.15
2024-10-01 | 8.15
2024-11-01 | 8.2
2024-12-01 | 7.9
Formulas:
Inherent Risk Level = EDATE([Inherent Risk Level, row above],RiskTimeline!$C3)
Pivot Calculations for Dashboard

## RiskTimeline
Timeline start | 2024-01-01
Interval (months) | 1
Timeline area
Risk Status | (Multiple Items)
|  |  |  | Average Risk Score | 11.3 | 10.5 | 9.65 | 9.65 | 9.55 | 9 | 8.15 | 8.15 | 8.15 | 8.15 | 8.2 | 7.9
Risks | Inherent Risk | Residual Risk | Date when Risk Score Changes | Date | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01
1 | 5 | 5 | 2030-01-01 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
2 | 8 | 8 | 2030-01-01 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | 15 | 4 | 2024-05-08 |  | 15 | 15 | 15 | 15 | 15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
4 | 16 | 2 | 2030-01-01 |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
5 | 25 | 8 | 2024-02-06 |  | 25 | 25 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
6 | 4 | 2 | 2023-10-19 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
7 | 5 | 1 | 2023-09-11 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | 4 | 4 | 2030-01-01 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
9 | 12 | 4 | 2030-01-01 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
10 | 15 | 8 | 2030-01-01 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
11 | 3 | 4 | 2024-10-02 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4
12 | 10 | 4 | 2024-11-30 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4
13 | 15 | 8 | 2024-12-05 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
14 | 20 | 4 | 2024-01-19 |  | 20 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
15 | 25 | 8 | 2024-06-06 |  | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 8 | 8 | 8 | 8 | 8
16 | 5 | 2 | 2024-12-12 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
17 | 10 | 8 | 2024-04-11 |  | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
18 | 15 | 6 | 2023-12-19 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
19 | 20 | 4 | 2023-12-12 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
20 | 25 | 25 | 2030-01-01 |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Risk Resolution Timeline
(For average Risk Score chart)

## Rating factors
Impact Level | Impact Rating | Description
-- Select Impact -- | --- Error ---
Very Low | 1 | Negligible impact. Minimal disruption to operations, no significant financial loss, and no material effect on customers or assets.
Low | 2 | Limited impact. Minor operational disruption, small financial loss, minor degradation of service or assets, or minimal customer/user impact.
Moderate | 3 | Noticeable impact. Significant operational degradation, moderate financial loss, or noticeable effect on customer experience or critical assets.
High | 4 | Severe impact. Major operational disruption, substantial financial loss, critical system or service downtime, or serious negative effect on customers or stakeholders.
Very High | 5 | Extreme impact. Multiple critical systems affected, catastrophic financial loss, major customer or reputational damage, or significant breach of data security.
Note: The impact levels are adapted version of the one in NIST's SP 800-30 Guide for Conducting Risk Assessments
Likelihood Level | Likelihood Rating | Description
-- Select Likelihood -- | --- Error ---
Rare | 1 | These risks have a low probability of occurring, as the name suggests.
Unlikely | 2 | Unlikely risks have an 11-40 percent chance of occurring, and it’s wise to monitor them.
Possible | 3 | Possible risks have a 41-60 percent chance of occurring and may happen about half the time, needing attention.
Likely | 4 | Likely risks have a 61-90 percent chance of occurring. They require regular attention and a consistent strategy.
Highly Likely | 5 | Risks in this category are almost certain to occur, with a likelihood of 91 percent or more.
Risk Rating | Risk Level
0 | --- Error ---
1 | Low
2 | Low
3 | Low
4 | Low
5 | Medium
6 | Medium
8 | Medium
9 | Medium
10 | Medium
12 | Medium
15 | Medium
16 | Medium
20 | High
25 | High

## Dropdowns
Risk Response Type
-- Select Risk Response --
Accept
Avoid
Mitigate
Transfer
Risk Status
-- Select Risk Status --
Open
In Progress
Closed
Task Status
-- Select Task Status --
Not Started
In Progress
On Hold
Closed
Risk Category | Category Description
-- Select Risk Category -- | Select the applicable cyber or operational risk category relevant to the SaaS business environment.
Data Breach | Risk of unauthorized access, disclosure, or theft of customer data, intellectual property, or sensitive business information stored in cloud platforms or internal systems.
Ransomware | Risk of malware or ransomware attacks affecting cloud infrastructure, endpoints, or production environments, potentially disrupting service availability and causing financial loss.
Insider Threats | Risk arising from employees, contractors, or privileged users misusing access to source code, customer data, or internal systems, either maliciously or accidentally.
Supply Chain | Risk stemming from third-party vendors, cloud service providers, SaaS integrations, or outsourced development partners that may introduce security weaknesses.
System Vulnerabilities | Risk related to unpatched software, insecure APIs, misconfigured cloud environments, or infrastructure weaknesses that could be exploited by threat actors.
Social Engineering | Risk of phishing, business email compromise (BEC), or impersonation attacks targeting employees, especially those with financial or administrative privileges.
Identity and Access | Risk of unauthorized system access due to weak authentication controls, poor role-based access management, or lack of multi-factor authentication (MFA).
Non-compliance | Risk of failing to comply with data protection laws (e.g., GDPR), contractual security obligations, or industry standards such as ISO 27001 or SOC 2.
Operational Disruption | Risk of service outages, cloud downtime, DDoS attacks, or infrastructure failures impacting SaaS platform availability and customer SLAs.
Response and Recovery | Risk of inadequate incident detection, response, disaster recovery, or business continuity planning, leading to prolonged downtime or reputational damage.
Mid-Size Technology Company (SaaS Provider)
Department | Description / Role in Risk Management
Information Technology (IT) | Manages infrastructure, networks, security systems, software development, and IT operations. Primary owner of most cybersecurity risks.
Sales | Handles customer accounts and data; exposed to risks like data breaches, compliance, and operational disruptions.
Finance | Responsible for financial systems, reporting, and payment processes; manages risks like fraud, ransomware, and vendor payment security.
Legal / Compliance | Ensures regulatory compliance, contract management, data protection, and internal policies; owner of non-compliance and contractual risks.
Procurement | Manages vendors, third-party software, and service contracts; oversees supply chain risks.
Human Resources (HR) | Handles employee onboarding, training, and insider threat mitigation; involved in social engineering and identity/access risks.
Customer Support / Operations | Ensures uptime and service delivery; exposed to operational disruption risks and SLA compliance.